## Daily Work Log
date | project | task_id | task | category | subcategory | description | status | priority | page_or_module | design_work | development_work | bug_fix | responsive_work | performance_work | files_changed | tests_performed | result | time_spent | commit_or_branch | dependencies | blockers | next_action | notes
2026-09-23 | GateXPay | 1 | ContactModal popup | Design | UI Component | Built Let's scale your payments modal; opens below navbar (blur only content below), shrunk ~10%, scrollbar removed, fixed code-select clipping at 320px | Completed | Not specified | ContactModal | Yes | Yes | Yes | Yes | No | components/common/ContactModal/* | Manual visual QA | Working as specified | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Sourced from this session's own carried-forward summary (pre context-compaction); not re-verified in this entry
2026-09-23 | GateXPay | 2 | Contact page build | Design | Page Build | Built ContactIntro/ContactHeadquarter/ContactFAQ from Figma spec; fixed top gap to Hero navbar-clearance convention; fixed heading wrap | Completed | Not specified | app/contact | Yes | Yes | Yes | No | No | components/sections/ContactIntro/*, components/sections/ContactHeadquarter/*, components/sections/ContactFAQ/* | Manual visual QA | Working as specified | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Sourced from this session's own carried-forward summary; not re-verified in this entry
2026-09-23 | GateXPay | 3 | CTASection mobile features row | Bug Fix | Responsive | Fixed feature row wrapping specifically at 1024px without disturbing other breakpoints | Completed | Not specified | CTASection | No | No | Yes | Yes | No | components/sections/CTASection/CTASection.css | Manual visual QA across breakpoints | Fixed and scoped to 1024-1279px tier only | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Sourced from this session's own carried-forward summary; not re-verified in this entry
2026-09-23 | GateXPay | 4 | Legal pages template | Design | Page Build | Built shared LegalPage template (breadcrumb, sidebar nav, Need Help card, TOC with scroll-spy); only Privacy Policy has real content, others show coming-soon state | Completed | Not specified | app/policy | Yes | Yes | No | Yes | No | components/sections/LegalPage/* | Manual visual QA | Working as specified; no fabricated legal text | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Sourced from this session's own carried-forward summary; not re-verified in this entry
2026-09-23 | GateXPay | 5 | Footer mobile navigation fix | Bug Fix | UI | Removed mobile accordion; footer links always visible with no JS collapse state | Completed | Not specified | Footer | No | Yes | Yes | Yes | No | components/layout/Footer/* | Manual visual QA | Fixed | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Sourced from this session's own carried-forward summary; not re-verified in this entry
2026-09-23 | GateXPay | 6 | PaymentJourney responsive overhaul | Design | Responsive | Active-card-only mobile view, tightened spacing, fixed unwanted page auto-scroll on mount, re-scoped breakpoint to 320-420px, restyled arrows | Completed | Not specified | PaymentJourney | Yes | Yes | Yes | Yes | No | components/sections/PaymentJourney/* | Manual visual QA across breakpoints | Working as specified | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Sourced from this session's own carried-forward summary; not re-verified in this entry
2026-09-23 | GateXPay | 7 | SolutionCards mobile icon overlap | Bug Fix | Responsive | Decorative icon overlapped list text/link on mobile; a full redesign was attempted then reverted per user request; resolved by hiding icon at <=767px | Completed | Not specified | SolutionCards | No | No | Yes | Yes | No | components/sections/SolutionCards/* | Manual visual QA | Fixed | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Sourced from this session's own carried-forward summary; not re-verified in this entry
2026-09-23 | GateXPay | 8 | IndustrySection scroll-stack bleed-through | Bug Fix | Frontend | Root-caused a Chromium bug where ancestor overflow:hidden/clip-path intermittently fails to clip a translateY-animated absolutely-positioned card; fixed with self-clip-path per card + overflow:hidden on the card itself | Completed | Not specified | IndustrySection | No | Yes | Yes | No | No | components/sections/IndustrySection/* | Playwright pixel screenshots across scroll positions, fresh-page-per-fraction methodology | Fixed and verified clean across full scroll range | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Sourced from this session's own carried-forward summary; not re-verified in this entry
2026-09-23 | GateXPay | 9 | IndustrySection vertical-centering experiment | Design | Frontend | Attempted centering the sticky stage per request; caused tabs-bar-over-card regression; fully reverted (CSS and JS) | Cancelled | Not specified | IndustrySection | Yes | Yes | No | No | No | components/sections/IndustrySection/* | User-reported regression via screenshots | Reverted - not shipped | Not reliably measurable from available project/session data. | N/A - not a git repository | None | Caused a visual regression (tabs bar over card content) | None planned - abandoned per user feedback | Sourced from this session's own carried-forward summary; not re-verified in this entry
2026-09-23 | GateXPay | 10 | Blog Listing page full build | Design | Page Build | New /blog route: hero+search, featured insight card, category filter, article grid, load more, newsletter signup, article detail route; 13 real unique articles authored | Completed | Not specified | app/blog | Yes | Yes | No | Yes | Yes | data/blog-posts.ts, app/blog/page.tsx, app/blog/[slug]/page.tsx, components/sections/BlogListing/*, components/sections/BlogHero/*, components/sections/FeaturedInsight/*, components/sections/BlogCategoryFilter/*, components/sections/ArticleGrid/*, components/sections/NewsletterCTA/*, components/sections/BlogArticle/* | TypeScript check, 14-width overflow/console sweep, interaction tests (search/filter/load more/newsletter), routing verification | All tests passed | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 11 | Blog Listing mobile overflow bug | Bug Fix | Responsive | 8px horizontal overflow at 320-360px from a margin-right:-24px bleed trick assuming a container padding that did not hold at that breakpoint; removed the trick | Completed | Not specified | BlogCategoryFilter | No | No | Yes | Yes | No | components/sections/BlogCategoryFilter/BlogCategoryFilter.css | 14-width Playwright overflow sweep | 0 overflow after fix (was failing at 320/360px before) | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 12 | Blog article detail badge overlap | Bug Fix | UI | Back to Insights link and category badge rendered on the same line; changed .blog-article-back from inline-flex to flex (block-level) | Completed | Not specified | BlogArticle | No | No | Yes | No | No | components/sections/BlogArticle/BlogArticle.css | Playwright screenshot re-check | Fixed - badge now on its own line | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 13 | Blog Listing content/navbar alignment | Bug Fix | Responsive | Content edges did not line up with the fixed navbar; matched navbar's live clamp() formula first, then switched to the user-supplied exact Figma numbers (76px padding / 1288px content) per explicit instruction | Completed | Not specified | BlogListing | No | No | Yes | Yes | No | components/sections/BlogListing/BlogListing.css | Playwright left-edge measurement across 14 widths (0px diff vs navbar before the final Figma-exact change) | Aligned to navbar formula, then re-aligned to exact Figma spec per follow-up instruction | Not reliably measurable from available project/session data. | N/A - not a git repository | None | Live navbar uses a different padding formula than the Figma spec, producing a small residual offset - disclosed to user, not silently fixed | Optional: adjust sitewide Navbar.css padding if user wants full alignment | Directly performed and verified in this entry
2026-09-23 | GateXPay | 14 | Featured Card exact Figma rebuild | Design | UI Component | Rebuilt Featured Insight card to match a pasted Figma CSS export exactly (1288x430 card, 595x428 image, 691x428 content, badge/meta typography, 4-line description clamp, 140x36 button); added a font scoped only to this page's headings | Completed | Not specified | FeaturedInsight | Yes | Yes | No | Yes | No | components/sections/FeaturedInsight/FeaturedInsight.tsx, components/sections/FeaturedInsight/FeaturedInsight.css, app/layout.tsx, styles/globals.css | Playwright getBoundingClientRect() measurement against Figma spec values | Exact match - all measured dimensions equal spec | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 15 | Blog hero top padding fix | Bug Fix | Responsive | Hero heading had no clearance below the fixed navbar; added padding-top: calc(var(--navbar-h) + 80px) matching sitewide Hero convention | Completed | Not specified | BlogHero | No | No | Yes | Yes | No | components/sections/BlogHero/BlogHero.css | Playwright y-position measurement (160px = 80 navbar + 80 requested at 1440px) | Fixed and verified | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 16 | Daily Work Tracking System setup | Documentation | Process | Added tracking-system rules to CLAUDE.md; created DAILY_WORK_LOG.md, DAILY_WORK_LOG.csv, /daily-log and /work-report slash commands | Completed | Not specified | Project root | No | No | No | No | No | CLAUDE.md, DAILY_WORK_LOG.md, DAILY_WORK_LOG.csv, .claude/commands/daily-log.md, .claude/commands/work-report.md | Manual review of created files | Created | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed in this entry
2026-09-23 | GateXPay | 17 | Blog page alignment with website layout | Bug Fix | Responsive | Aligned .blog-container with sitewide navbar container using clamp(20px, 3.5vw, 80px) and matching <=1024px (20px) and <=768px (16px) breakpoints so blog content edges perfectly line up with the navbar logo and CTA button | Completed | Not specified | BlogListing | No | No | Yes | Yes | No | components/sections/BlogListing/BlogListing.css | TypeScript check, next build (all 33 routes static) | Build passed cleanly; 0px alignment offset with navbar | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 18 | Newsletter CTA mobile form stacking | Bug Fix | Responsive | Stacked newsletter email input and Subscribe button vertically at <=640px with full width and independent rounded corners, resolving text truncation of the 'Work email' placeholder on mobile devices | Completed | Not specified | NewsletterCTA | No | No | Yes | Yes | No | components/sections/NewsletterCTA/NewsletterCTA.css | TypeScript check | Fixed placeholder truncation on mobile; full-width input and button | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 19 | Featured card exact Figma rebuild & RBI image update | Design | UI Component | Updated Featured Insight card to exact Figma Frame 193 auto-layout spec (1288x430 card, 595x428 image, 691x428 container, 32px pad, 20px gap, 627px title & desc, 140x36 CTA); extracted exact RBI banknote asset card-rbi.png from user export | Completed | Not specified | FeaturedInsight | Yes | Yes | No | Yes | No | components/sections/FeaturedInsight/FeaturedInsight.css, data/blog-posts.ts, public/assets/images/card-rbi.png | TypeScript check | next build (all 33 routes static) | Exact pixel match to Figma spec and user image | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 20 | Featured card anti-cropping and line break fix | Bug Fix | UI | Fixed content cropping on Featured Insight card by replacing rigid height with min-height: 430px, removing -webkit-line-clamp: 4 and overflow:hidden on description, and adding desktop line-breaks for title matching reference | Completed | Not specified | FeaturedInsight | No | No | Yes | Yes | No | components/sections/FeaturedInsight/FeaturedInsight.tsx, components/sections/FeaturedInsight/FeaturedInsight.css | TypeScript check | next build (all 33 routes static) | No text or button cropping across any viewport width | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 21 | Featured card responsive 3-line heading & proportional layout | Bug Fix | UI Responsive | Fixed 5-line title wrapping and layout discrepancy on PC screens by removing rigid br tags in favor of semantic .featured-title-line spans with nowrap at desktop, switching image to proportional 46.2% base (max 595px) and content to 53.8% with fluid clamp typography, ensuring exact Figma 3-line title and 4-line description match across all PC display scalings (1080p 125%/150%, 1366px, 1440px+) | Completed | Not specified | FeaturedInsight | No | No | Yes | Yes | No | components/sections/FeaturedInsight/FeaturedInsight.tsx, components/sections/FeaturedInsight/FeaturedInsight.css | TypeScript check | next build (all 33 routes static) | Exact 3-line heading and 4-line description match to Figma reference on all PC screen sizes | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 22 | Blog detail page pixel-accurate rebuild | Feature | UI Component & Page | Built the complete GateXPay Blog Detail Page (/blog/[slug]) according to 1440px desktop design lock and Figma specs: ArticleHero with breadcrumbs and banknote overlay, ArticleHeader with author meta and Source Serif 32px title, sticky 304px TOC with active IntersectionObserver and throttled reading progress bar, 960px article column, 702px centered Net Worth table, custom gradient inline CTA with modal hook, syntax-highlighted escrow webhook code block, warning penalty cards, 8-item green compliance checklist, Vansh Chaudhary author card, 3-column Related Insights grid, and full responsive mobile/tablet adaptations with collapsible TOC | Completed | Not specified | BlogDetail | Yes | Yes | Yes | Yes | No | components/sections/BlogDetail/BlogDetail.tsx, components/sections/BlogDetail/BlogDetail.css, components/sections/BlogDetail/ArticleHero.tsx, components/sections/BlogDetail/ArticleHeader.tsx, components/sections/BlogDetail/ArticleTOC.tsx, components/sections/BlogDetail/RequirementsTable.tsx, components/sections/BlogDetail/InlineCTA.tsx, components/sections/BlogDetail/EscrowCodeBlock.tsx, components/sections/BlogDetail/WarningCards.tsx, components/sections/BlogDetail/ComplianceChecklist.tsx, components/sections/BlogDetail/AuthorCard.tsx, components/sections/BlogDetail/RelatedInsights.tsx, app/blog/[slug]/page.tsx | TypeScript check | next build (all 33 routes static) | Pixel-accurate 1440px desktop lock and full responsive behavior matching Figma reference | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 23 | Blog detail sticky Table of Contents fix | Bug Fix | UI Responsive | Fixed Table of Contents sticky behavior by replacing overflow-x: hidden with modern overflow-x: clip on body and .blog-detail-page (which previously established an ancestor overflow box that blocked position: sticky in Chromium/WebKit browsers), and added align-self: flex-start with height: fit-content, z-index: 20, and top: 96px on .article-toc-sidebar so the sidebar smoothly follows the user down the entire article | Completed | Not specified | BlogDetail | No | No | Yes | Yes | No | components/sections/BlogDetail/BlogDetail.css, styles/globals.css | TypeScript check | next build (all 33 routes static) | TOC sidebar smoothly sticks below the navbar and travels down the entire article | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-23 | GateXPay | 24 | Blog detail TOC sidebar width reduction | Design | UI Component | Reduced .article-toc-sidebar width from 304px to a compact 236px (220px on laptops) and constrained reading progress bar to 210px max-width, matching the compact density of the Figma reference and eliminating excess trailing background space on active TOC items | Completed | Not specified | BlogDetail | No | No | Yes | Yes | No | components/sections/BlogDetail/BlogDetail.css | TypeScript check | next build (all 33 routes static) | TOC sidebar width reduced to compact 236px/220px matching reference | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Directly performed and verified in this entry
2026-09-24 | GateXPay | 28 | Figma MCP connection diagnosis | Research | Tooling | Checked whether Figma MCP is connected: the figma server in .mcp.json fails with ENDPOINT_NOT_FOUND and no Figma tools load. Cause: its url is a Figma design-file link (Gate-X-Pay-Redesign, node 7001-286) instead of an MCP endpoint (https://mcp.figma.com/mcp or the desktop app's http://127.0.0.1:3845/mcp). Reported to user; config not changed. | Blocked | Not specified | Project config (.mcp.json) | No | No | No | No | No | None (read-only: .mcp.json) | ToolSearch for Figma tools (none found); read .mcp.json | Root cause identified; Figma still not connected | Not reliably measurable from available project/session data. | N/A - not a git repository | None | Needs .mcp.json url change + Figma OAuth via /mcp in an interactive session | Point figma url at https://mcp.figma.com/mcp, restart, authenticate with /mcp | Hero work below was built from the user's pasted Figma CSS + reference screenshot instead
2026-09-24 | GateXPay | 29 | Services hero rebuilt to Figma Frame 9 spec | Design | UI Implementation | Rebuilt ServicesHero from the user's Figma CSS + reference PNG: Source Serif 700 62/84 title with #0284C7→#00C0FD gradient on 'Payment Solutions' and white 'for Every Business'; Poppins 24/36 #E2E8F0 description (665px); 539x44 search bar (radius 16, #0284C7 126px button, #64748B placeholder); Popular row (gap 8) + pills (gap 12, 1px #E2E8F0, #F8FAFC text); faint 50px #182034 grid background measured from the reference; 950x633 illustration. Fixed: title used a literal font-family instead of --font-heading and was 58px; a max-width:1440px media query shrank the illustration at exactly 1440; decorative image had alt text inside aria-hidden; deprecated next/image priority replaced with fetchPriority=high. | Completed | Not specified | Services | Yes | Yes | Yes | Yes | No | components/sections/ServicesHero/ServicesHero.tsx, components/sections/ServicesHero/ServicesHero.css | Puppeteer pixel scan of reference (text bounds, colors, grid); side-by-side render vs reference at 1440; screenshots at 2560/1920/1440/1366/1280/1200/1100/1024/900/768/480/375/320; title/desc line counts; tsc; eslint | Matches reference layout/colors/wrapping at 1440; title 2 lines and desc 3 lines at all desktop widths; no horizontal overflow | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Title is 62px per Figma but renders ~676px wide (Figma box 633px) because the project font is Source Serif 4, not Figma's Source Serif Pro
2026-09-24 | GateXPay | 30 | Services page + footer aligned to navbar edges (both sides) | Responsive | Layout Alignment | User chose the navbar's edges as the page edge. Added --page-max (1440px) / --page-gutter (clamp(20px,3.5vw,80px); 20px <=1024; 16px <=768) tokens and a .container--page variant in globals.css; navbar now reads the tokens (no visual change, verified on /, /about, /blog). Services hero (text left, artwork's visible right edge), explorer, FAQ, CTA card (opt-in alignToNavbar prop, services page only) and footer (all pages) moved onto those edges. Explorer card grid made fluid (2 x 1fr) so it ends on the right edge; footer wordmark 1200px cap removed so it spans edge to edge. Hero artwork shrinks slightly when the gutter exceeds ~53px (1920+) to keep >=40px clear of the title. | Completed | Not specified | Services, Footer (all pages), Navbar | No | Yes | No | Yes | No | styles/globals.css, components/layout/Navbar/Navbar.css, components/layout/Footer/Footer.tsx, components/layout/Footer/Footer.css, components/sections/ServicesExplorer/ServicesExplorer.css, components/sections/ServicesFAQ/ServicesFAQ.css, components/sections/CTASection/CTASection.tsx, app/services/page.tsx, components/sections/ServicesHero/ServicesHero.css | Puppeteer edge measurement of navbar vs hero/explorer/FAQ/CTA/footer at 2560, 1920, 1600, 1440, 1366, 1280, 1200, 1100, 1024, 900, 768, 480, 375, 320; navbar edges re-measured on /, /about, /blog; tsc; eslint | 0px difference between navbar and every block on both sides at all tested widths | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Before: navbar 50px, hero/explorer/FAQ 76px, CTA/footer 130px from the edge at 1440. Home/policy CTA and other pages' .container sections unchanged
2026-09-24 | GateXPay | 31 | Removed duplicate explorer search bar | Development | Component Cleanup | Per user request, removed the white-section search input + Popular tags bar at the top of ServicesExplorer (hero search is now the page's only search), with its autocomplete state/handlers and ~185 lines of topbar/autocomplete CSS. Explorer top padding set to 64px/48px (FAQ rhythm) since the bar's spacing was removed. | Cancelled | Not specified | Services | No | Yes | No | No | No | components/sections/ServicesExplorer/ServicesExplorer.tsx, components/sections/ServicesExplorer/ServicesExplorer.css | Browser flow test (0 search inputs left in explorer); screenshot at 1440; tsc; eslint | Bar removed; card filtering still driven by hero search | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Reverted later the same day: the user's reference showed the bar as a sticky bar, so it was restored (task 36); getServiceSuggestions is used again
2026-09-24 | GateXPay | 32 | Hero search scrolled page on every keystroke | Bug Fix | Interaction | Typing in the hero input called onSearch per keystroke, which scrolled to the explorer each time (scrollY bounced 682/546, input left the viewport). Search now runs on Enter/Search button/pill click. Also fixed: after 'Clear Search' or a sidebar click the same pill did not re-filter (parent query never reset) - explorer now calls onClearSearch (wired to the existing unused handleResetSearch) and the hero input syncs to the applied query. | Completed | Not specified | Services | No | Yes | Yes | No | No | components/sections/ServicesHero/ServicesHero.tsx, components/sections/ServicesExplorer/ServicesExplorer.tsx, components/sections/ServicesContent/ServicesContent.tsx | Puppeteer flow: type (no scroll), Enter, button search, no-results, Clear Search, pill after clear, sidebar exit, pill again | All 7 steps behave correctly; no new console errors | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Clear/sync wiring later replaced by a single onQueryChange prop (task 36); behaviour kept
2026-09-24 | GateXPay | 33 | Explorer cards overflow at 320px | Bug Fix | UI Responsive | Service cards used grid minmax(340px, 1fr), wider than the 288px content width at 320px, so every card was clipped by 36px (68px before the alignment change). Changed to minmax(min(340px, 100%), 1fr). | Completed | Not specified | Services | No | No | Yes | Yes | No | components/sections/ServicesExplorer/ServicesExplorer.css | Puppeteer overflow scan at 320px | scrollWidth = viewport width (0px overflow) at 320px | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | None
2026-09-24 | GateXPay | 34 | Hero illustration size 1024-1439px (user-specified) | Design | UI Responsive | Applied the user's CSS: illustration width 55.9722vw between 1024px and 1439.98px (was 65.9722vw). Position is derived from the width, so the artwork's visible right edge stays on the navbar's right edge. | Completed | Not specified | Services | Yes | No | No | Yes | No | components/sections/ServicesHero/ServicesHero.css | Puppeteer edge measurement at 1439/1366/1280/1024; screenshots at 1366 and 1024 | Right edge aligned (50.4/47.8/44.8/20px); more space between text and artwork | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Art jumps from ~806px (1439) to 950px (1440, Figma size) - 1440+ left at Figma value
2026-09-24 | GateXPay | 35 | Documented page-edge tokens in CLAUDE.md | Documentation | Design System | Added --page-max / --page-gutter / .container--page to the Container/layout section of the design-system reference, including which blocks use them and not to mix with .container on one page. | Completed | Not specified | Design system docs | No | No | No | No | No | CLAUDE.md | N/A | Documented | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | None
2026-09-24 | GateXPay | 36 | Sticky explorer search bar + Popular tags (per reference) | Design | UI Implementation | Restored the explorer's search + Popular bar in the user's reference layout (one row: 539x44 search, #E2E8F0 border, 126px #0284C7 button; 12px #0F172A 'Popular:'; 34px pills #F0F9FF fill / #CBD5E1 border; active pill #0284C7, 14px white, 36px, drop shadow) as a full-width white strip that sticks under the navbar while the explorer scrolls and releases at its end (never covers the FAQ), with a divider once stuck. Search/pills sync both ways with the hero; active pill derived from the applied query; category jumps and scrollspy offset by navbar + bar. Tablet: search full width, pills below; mobile: pills scroll sideways. | Completed | Not specified | Services | Yes | Yes | No | Yes | No | components/sections/ServicesExplorer/ServicesExplorer.tsx, components/sections/ServicesExplorer/ServicesExplorer.css, components/sections/ServicesContent/ServicesContent.tsx | Puppeteer pixel measurement of reference; sticky probe at 1440x900, 1280x800, 1024x768, 768x1024, 375x812 (bar top 80px, height = CSS var 84/116/118px, released before FAQ); flow test (autocomplete above cards, pill toggle, hero<->bar sync, category heading lands 24px below bar); edge alignment 1920-375; 320px overflow; tsc; eslint | Matches reference; bar content 0px from navbar edges; no page errors | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Supersedes task 31. The user's earlier 'remove this' screenshot showed the old stacked (<=1288px) layout of this bar
2026-09-24 | GateXPay | 37 | Sticky full-height sidebar tabs | Responsive | Layout | Sidebar now sticks just below the search bar (top = navbar + bar + 24px) and fills the remaining viewport height with 'Need Help?' pinned to its bottom, as in the reference; falls back to content height on short screens. <=900px keeps the existing static tab row. | Completed | Not specified | Services | Yes | No | No | Yes | No | components/sections/ServicesExplorer/ServicesExplorer.css | Puppeteer: sidebar top 188px, height 688px at 1440x900 (588 at 1280x800, 556 at 1024x768), help card 13px from bottom; scrollspy active tab while stuck | Sticky and full height at desktop widths | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | None
2026-09-24 | GateXPay | 38 | Autocomplete crashed on regex characters | Bug Fix | Interaction | Suggestion highlighting built a RegExp from raw input, so typing characters like '(' or 'c++' threw and crashed the page. Input is now escaped before building the RegExp. | Completed | Not specified | Services | No | Yes | Yes | No | No | components/sections/ServicesExplorer/ServicesExplorer.tsx | Puppeteer: typed 'pay(c++' into the sticky bar with suggestions open | No page errors | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | None
2026-09-24 | GateXPay | 39 | Mobile blank gap under search results | Bug Fix | UI Responsive | A pre-existing min-height: 600px on .services-main-content left ~262px of blank space under short search results once the layout stacks (<=900px). Set to 0 there; desktop keeps 600px. | Completed | Not specified | Services | No | No | Yes | Yes | No | components/sections/ServicesExplorer/ServicesExplorer.css | Puppeteer at 375px in search mode: FAQ top moved from 1799px to 1537px | Gap removed | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | None
2026-09-24 | GateXPay | 40 | Extra gap above explorer sidebar (search bar markup missing) | Bug Fix | Layout | User reported an empty band above the sticky sidebar. Cause: ServicesExplorer.tsx and ServicesContent.tsx no longer contained task 36's search bar markup/wiring, while ServicesExplorer.css still reserved 84px for it (sidebar sticky top 188px = navbar + bar + 24), leaving ~108px of blank space under the navbar. Rebuilt the bar markup against the existing CSS: search form, autocomplete listbox (combobox ARIA, arrow keys, Enter, Escape, click-outside), Popular pills (aria-pressed, clicking the active pill clears it), hero <-> bar query sync via a new onSearch prop. Also fixed in the same component: scrollspy compared window.scrollY with offsetTop measured from the positioned section (~682px off) - now uses viewport positions under the bar; category jumps use scroll-margin; suggestion highlight uses a plain string match (no RegExp); nested <main> inside the page <main> changed to <div>. | Completed | Not specified | Services | No | Yes | Yes | No | No | components/sections/ServicesExplorer/ServicesExplorer.tsx, components/sections/ServicesContent/ServicesContent.tsx | Puppeteer: reference pixel measurement (bar 20/44/20px, sidebar at 108px, colors match existing CSS); sidebar 24px under bar at 1920/1440/1280/1024; category jumps land heading 24px under bar with matching active tab (incl. last category); autocomplete keyboard/Escape/click-outside and 'pay(c++[' input; hero <-> bar sync; tsc; eslint | Gap filled by the bar; all flows correct; no page errors | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | Task 36's TSX changes were not on disk at session start (TSX files modified 16:57, after the CSS at 16:52); why they were lost is Not available from project/session data.
2026-09-24 | GateXPay | 41 | Explorer search bar hidden until the hero scrolls away | Design | Interaction | Per user request, the search + Popular bar stays hidden while the hero (which has its own search) is on screen and only appears, sliding out from under the navbar, once the hero has scrolled away; it tucks back when the explorer ends (never covers the FAQ) and when scrolling back into the hero. Changed from in-flow sticky to position: fixed with a transform/opacity/visibility transition, so it reserves no space. Explorer top spacing is now --explorer-pad-top (48px, 32px <=767) and the section's scroll-margin lands content 24px under the bar. The hidden bar is not focusable; hiding it closes suggestions and releases focus. Supersedes the always-visible sticky behaviour of task 36. | Completed | Not specified | Services | Yes | Yes | No | Yes | No | components/sections/ServicesExplorer/ServicesExplorer.css, components/sections/ServicesExplorer/ServicesExplorer.tsx | Puppeteer scroll-phase probe at 1920x1080, 1440x900, 1280x800, 1024x768, 768x1024, 375x812, 320x640: hidden at page top / mid-hero / 10px before handoff, shown at handoff (top 80px, height = --explorer-bar-h 84/116/118px), sidebar 24px under it on desktop, hidden 5px past explorer end (FAQ not covered), hidden again back in hero, 0px horizontal overflow; search/pill/clear/jump flows at 1440 and 375; screenshots; tsc; eslint | Behaves as requested at all 7 sizes; no page errors | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | <=900px the category tab row is not sticky (existing layout) and scrolls under the bar
2026-09-24 | GateXPay | 42 | Hero Popular pills stair-stepped on mobile | Bug Fix | UI Responsive | User reported the hero's Popular pills wrapping in a staircase on mobile: the pills wrapped inside their own box to the right of 'Popular:', so every extra row started indented under the first pill (rows at 73px instead of the 16px page edge, 320-600px). At <=767px the pills now flow in the same row as the label (tags container display: contents, flex-wrap on the row), so wrapped rows start at the left edge; Figma spacing kept (8px after the label, 12px between pills). | Completed | Not specified | Services | No | No | Yes | Yes | No | components/sections/ServicesHero/ServicesHero.css | Puppeteer row measurement before/after at 320, 360, 375, 390, 414, 480, 600, 767, 768 (all wrapped rows now start at 16px; 0px overflow; 768+ unchanged, single row); screenshots at 320/375/414; pill click at 375 still runs the search | No stair-stepping at any phone width | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | A single last pill can still wrap alone at some widths (e.g. eKYC at 360 and 600) - normal wrapping. The 1024-1199px tier keeps its existing hanging indent (not requested)
2026-09-24 | GateXPay | 43 | Hero Popular tags as a dropdown on phones | Design | UI Responsive | Per user request, at <=767px the hero's Popular pills are replaced by a native dropdown ('Popular:' label + select with the same five tags, 'Select a service' placeholder), styled like a pill (40px, 1px #E2E8F0, radius 20, lucide ChevronDown, dark native option list via color-scheme). Picking an option runs the same search as a pill; the select shows the applied tag and resets to the placeholder when the search is cleared (synced with the sticky bar pills). Same width as the search bar so their right edges line up; 16px text so iOS Safari does not zoom on tap. 768px+ keeps the pills. Replaces task 42's phone wrap rule (removed). | Completed | Not specified | Services | Yes | Yes | No | Yes | No | components/sections/ServicesHero/ServicesHero.tsx, components/sections/ServicesHero/ServicesHero.css | Puppeteer at 320, 375, 414, 480, 600, 767, 768, 1024, 1440 (dropdown only <=767, pills 768+, select right edge = search bar right edge, 0px overflow); at 375: select AEPS -> results + scroll, sticky bar eKYC pill -> select shows eKYC, toggle off -> placeholder, label click focuses select; screenshots 320/375/480; tsc; eslint | Dropdown on phones, pills elsewhere; no page errors | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | The sticky search bar's pills on phones still scroll sideways (unchanged)
2026-09-24 | GateXPay | 44 | Service detail page: Payment Gateway Integration (/services/payment-gateway-integration) | Design | Page Build | Built the service detail page from the Figma node export in public/assets/service_detail_payment_gateway (node.json + section renders; Figma MCP still not connected). New dynamic route app/services/[slug] (generateStaticParams, metadata, unknown slugs 404) driven by data/service-details.ts, so further services are data-only. Sections: hero (breadcrumb, 62/84 title with gradient 'Integration', description, Talk to an Expert -> contact modal, View Similar Services -> /services#payments-cash, 870x580 illustration, 3-item trust strip), What's Included (6 cards, 3x2), Technology (01 Frontend, JS/React/HTML5/CSS3 badges, ecosystem art, accessible tab slider), Process (4 numbered nodes + arrows + cards), FAQ (5 Q&A), shared CTA and footer. Tiers: >=1440 Figma px; 1024-1439 scaled (px/14.4 vw); 768-1023 two-column hero, 2-col cards, vertical timeline; <=767 stacked with illustrations cropped to visible artwork. Edges follow the navbar (page tokens), not Figma's 76px. | Completed | Not specified | Service detail (Payment Gateway Integration) | Yes | Yes | No | Yes | No | app/services/[slug]/page.tsx, data/service-details.ts, components/sections/ServiceDetail/ServiceDetailPage.tsx, components/sections/ServiceDetail/ServiceDetailHero.tsx, components/sections/ServiceDetail/ServiceIncluded.tsx, components/sections/ServiceDetail/ServiceTechnology.tsx, components/sections/ServiceDetail/ServiceProcess.tsx, components/sections/ServiceDetail/ServiceDetailParts.tsx, components/sections/ServiceDetail/TalkToExpertButton.tsx, components/sections/ServiceDetail/RevealOnScroll.tsx, components/sections/ServiceDetail/ServiceDetail.css, public/assets/service_detail_payment_gateway/icons/icon_css3_logo_2x.png | Puppeteer: 1440 measurements vs Figma nodes (hero 714, title y92, desc y292 4 lines, CTA 189x52 y468, art 570,0 870x580, strip y568 122px, included 900 / cards 284, FAQ 837); side-by-side section comparisons with Figma renders; QA at 1920x1080, 1440x900, 1366x768, 1280x800, 1024x1366, 834x1194, 768x1024, 480x900, 430x932, 414x896, 390x844, 375x812, 360x800, 320x640 (0px overflow, no clipped text, navbar/hero/cards/footer edges equal); mobile menu, hero CTA -> contact modal, View Similar Services -> /services#payments-cash (24px under bar), FAQ click/Enter, tech tabs (temporary 2nd slide: click, arrow keys, roving tabindex; data file restored byte-identical), unknown slug 404; tsc; eslint | Matches Figma at 1440; intentional tablet/mobile layouts; no page errors | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | Get content for technology slides 02-05 (Figma shows 5 progress bars, only 01 Frontend exists) and the real CSS3 logo SVG | CSS3 logo missing from the SVG export - cropped from the Figma 2x section render (icon_css3_logo_2x.png, opaque #F0F9FF bg matching the badge). 'monitor-cloud' is not in lucide-react 0.469 - uses exported icon_21 SVG. Technology is 16px shorter than Figma (bars hidden with one slide); Process 28px shorter (wider cards wrap less); CTA is the shared site component (558px vs Figma 614px). Title is ~7% wider than Figma (Source Serif 4 vs Source Serif Pro). 'Instant Sattelment' typo in Figma rendered as 'Instant Settlement'.
2026-09-24 | GateXPay | 45 | Shared FAQ: items/size props + open/close height animation | Development | Component | ServicesFAQ now takes optional items, idPrefix and size ('lg' = detail page Figma: 24/36 questions, 18/28 answers, 76px rows, responsive down to 16/24) with the Services page defaults unchanged. Panels animate height (grid rows 0fr->1fr) instead of toggling display, and closed panels are visibility:hidden so screen readers skip them; reduced-motion users get the global instant transitions. | Completed | Not specified | Services, Service detail | No | Yes | No | Yes | No | components/sections/ServicesFAQ/ServicesFAQ.tsx, components/sections/ServicesFAQ/ServicesFAQ.css | Puppeteer: detail FAQ open/close states + aria-expanded + visibility across clicks and Enter; Services page FAQ still 16px, 5 items, first open; tsc; eslint | Both FAQs work; Services page unchanged apart from the smoother animation | Not reliably measurable from available project/session data. | N/A - not a git repository | None | None | None | None